## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17562 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000466/2023-2024 | 5360/MD | 30/11/2023 | 03/10/2025 | GOBINDA MAITY | 2125.38 | 322.43 | 15.17 | 46
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17562 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000030/2023-2024 | 1194/W/MMD | 25/04/2023 | 26/09/2025 | RISHAV ENTERPRISE | 22.95 | 6.86 | 29.9 | 80
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17562 | New | Material Requisition To Resource Division |  |  | RTOR000262/2023-2024 | 2011/MD | 16/05/2023 | 16/05/2023 | Resource Division | 37.87 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17562 | New | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 1462 | 08/05/2023 | 08/05/2023 | Resource Division | 13.6 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17562 | New | Electrict quotation bill for TW-II of Kashida(Zone-II) pwss (Ref Consumar ID-204378324),Application No-2004857302,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/02420/2024-2025 | C102415712702 | 05/10/2024 | 05/10/2024 | WBSEDCL | 3.17 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17562 | New | Electrict quotation bill for TW-I of Kashida(Zone-II) pwss (Ref Consumar ID-204377091),Application No-2004857217,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/02421/2024-2025 | C102415708399 | 05/10/2024 | 05/10/2024 | WBSEDCL | 5.63 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17562 | New | Construction of Approach Road (3m width) of Kashida (Zone-II) Piped Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000399/2024-2025 | 155/MD | 15/01/2025 | 14/02/2025 | GOBINDA MAITY | 2.63 | 0 | 0 | 100
Total | [13 empty] | 2211.23 | 329.29 | 14.89