## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | SM/17566 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 1453/MD | 08/05/2023 | 08/05/2023 | Resource Division | 23.16 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | SM/17566 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000031/2023-2024 | 1195/W/MMD | 25/04/2023 | 14/04/2025 | DEBJYOTI BASU | 22.64 | 14.12 | 62.34 | 40
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | SM/17566 | New | Electrict quotation bill for TW-I of Nilda pwss (Zone-II) (Ref Consumar ID-204310685),Application No-2004741431,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/01068/2024-2025 | BP-2024-25-198 | 24/05/2024 | 24/05/2024 | WBSEDCL | 9.92 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | SM/17566 | New | Electrict quotation bill for TW-II of Nilda pwss (Zone-II) (Ref Consumar ID-204310727),Application No-2004741416,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/01067/2024-2025 | BP-2024-25-197 | 24/05/2024 | 24/05/2024 | WBSEDCL | 7.26 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | SM/17566 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 28/12/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 69.06 | 1.87 | 55
Total | [13 empty] | 3762.81 | 83.17 | 2.21