## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17567 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Rabidaspur, Tiorberya & Ramchandrapur & its adjoining Mouzas PWSS instead Rabidaspur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000748/2022-2023 | 1267/MD | 23/06/2022 | 03/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.37 | 4.37 | 100 | 100
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17567 | New | Material Requisition To Resource Division |  |  | RTOR000252/2023-2024 | 1586/MD | 15/05/2023 | 15/05/2023 | Resource Division | 43.26 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17567 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000368/2023-2024 | 1694/W/MMD | 04/08/2023 | 01/09/2025 | A G ENTERPRISE | 78.38 | 0 | 0 | 20
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17567 | New | Sinking of Tube Well, Rising main, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 150 cum OHR (Intze type with pile foundation) & Accommodate FHTC (863 nos.) including 2 years of Operation & Maintenance under JJM with allied work for Rabidaspur PWSS in Daspur- I Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000391/2023-2024 | 5065/MD | 26/10/2023 | 12/10/2025 | ZENITH CONSTRUCTION | 310.14 | 0 | 0 | 10
Total | [13 empty] | 436.14 | 4.37 | 1