## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17572 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sautia & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000757/2022-2023 | 1112/MD | 09/06/2022 | 29/06/2022 | ENVIROTECH SOLUTIONS | 1.49 | 1.49 | 100 | 100
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17572 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000034/2023-2024 | 1198/W/MMD | 25/04/2023 | 14/04/2025 | DEBJYOTI BASU | 22.77 | 14.23 | 62.5 | 40
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17572 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 25/08/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 125.67 | 3.4 | 58
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17572 | New | Material Requisition To Resource Division |  |  | RTOR000259/2023-2024 | 2008/MD | 16/05/2023 | 16/05/2023 | Resource Division | 27.68 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17572 | New | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 1460 | 08/05/2023 | 08/05/2023 | Resource Division | 10.52 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17572 | New | Electrict quotation bill for TW-I of Sautia pwss (Zone-I) (Ref Consumar ID-204310821),Application No-2004741353,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/01069/2024-2025 | BP-2024-25-202 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.52 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17572 | New | Electrict quotation bill for TW-II of Sautia pwss (Zone-I) (Ref Consumar ID-204482861),Application No-2005024387,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/03900/2024-2025 | C022507784862 | 04/02/2025 | 04/02/2025 | WBSEDCL | 7.2 | 0 | 0 | 0
Total | [13 empty] | 3774.01 | 141.39 | 3.75