## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17573 | New | Material Requisition To Resource Division |  |  | RTOR000260/2023-2024 | 2009/MD | 16/05/2023 | 16/05/2023 | Resource Division | 24.11 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17573 | New | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 1459 | 08/05/2023 | 08/05/2023 | Resource Division | 7.86 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17573 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000035/2023-2024 | 1199/W/MMD | 25/04/2023 | 22/10/2023 | TAPAN KUMAR SARKAR | 22.62 | 12.77 | 56.44 | 50
Total | [13 empty] | 54.6 | 12.77 | 23.39