## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17575 | New | Material Requisition To Resource Division |  |  | RTOR000282/2023-2024 | 4054/MD | 12/10/2023 | 12/10/2023 | Resource Division | 32.99 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17575 | New | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 3389/MD | 25/11/2024 | 25/11/2024 | Resource Division | 7.18 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17575 | New | QUOTATION MONEY FOR TIORBERYA WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/17575, APPLICATION NO 2004826966, REFERENCE ID 204360838, DASPUR CCC, WBSEDCL |  |  | BILL/02043/2024-2025 | C082441589956 | 29/08/2024 | 29/08/2024 | WBSEDCL | 6.75 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17575 | New | QUOTATION MONEY FOR TIORBERYA WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/17575, APPLICATION NO 2004723249, REFERENCE ID 204300057, SONAKHALI CCC, WBSEDCL |  |  | BILL/00879/2024-2025 | BP-2024-25-182 | 20/05/2024 | 20/05/2024 | WBSEDCL | 5.68 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17575 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000368/2023-2024 | 1694/W/MMD | 04/08/2023 | 01/09/2025 | A G ENTERPRISE | 78.38 | 0 | 0 | 20
6 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/17575 | New | Sinking of Tube Well ,Laying Rising Main,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 100 cum OHR (Intze type foundation) & Accommodate FHTC (490nos) Including 2 years of Operation & Maintenance under JJM with allied work for Tiorberya PWSS in Daspur- I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000206/2023-2024 | 2822/MD | 07/08/2023 | 25/01/2026 | ZENITH CONSTRUCTION | 222.1 | 44.63 | 20.1 | 20
Total | [13 empty] | 353.07 | 44.63 | 12.64