## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | TALBANDI AND ITS ADJOINING MOUJAS PWSS | SM/17614 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TALBANDI AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002044/2022-2023 | 952/W/MMD | 28/03/2023 | 24/09/2023 | MASSK ENGINEERING WORKS | 21.58 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | TALBANDI AND ITS ADJOINING MOUJAS PWSS | SM/17614 | New | Sinking of Tube Well ,Laying of Rising Main ,Laying distribution pipe line, Pump House, 100 cum OHR( Intze type with solid raft ) & Accommodate FHTC (712 Nos) including 2 years operation & maintenance under JJM with allied work for Talbandi & its adjoining mouzas W/S scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000067/2023-2024 | 2148/MD | 08/06/2023 | 01/01/2025 | M/S. RAJ KUMAR KHAN | 239.9 | 39.49 | 16.46 | 45
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | TALBANDI AND ITS ADJOINING MOUJAS PWSS | SM/17614 | New | Material Requisition To Resource Division |  |  | RTOR000230/2023-2024 | 1518/MD | 12/05/2023 | 12/05/2023 | Resource Division | 20.4 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | TALBANDI AND ITS ADJOINING MOUJAS PWSS | SM/17614 | New | Electrict quotation bill for TW-II of Talbandi pwss (Ref Consumar ID-204450414),Application No-2004970827,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra |  |  | BILL/03248/2024-2025 | C122405706864 | 05/12/2024 | 05/12/2024 | WBSEDCL | 5.9 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | TALBANDI AND ITS ADJOINING MOUJAS PWSS | SM/17614 | New | Electrict quotation bill for TW-I of Talbandi pwss (Ref Consumar ID-204314575),Application No-2004747841,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra |  |  | BILL/01121/2024-2025 | BP-2024-25-234 | 04/06/2024 | 04/06/2024 | WBSEDCL | 3.85 | 0 | 0 | 0
Total | [13 empty] | 291.63 | 39.49 | 13.54