## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS | SM/17617 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOLEGRAM AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000014/2023-2024 | 1130/W/MMD | 12/04/2023 | 01/04/2025 | P.K.ENGINEERING | 25.25 | 12.32 | 48.78 | 50
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS | SM/17617 | New | Construction of 350 Cum & 300 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,209 Nos) including 2 years operation & maintenance For Golegram and Kanakpur Pipe water supply Scheme within Debra Block under Kharagpur Sub Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000386/2023-2024 | 5060/MD | 26/10/2023 | 27/12/2025 | IJABUL SEKH | 992.27 | 221.42 | 22.31 | 45
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS | SM/17617 | New | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 1583/MD | 15/05/2023 | 15/05/2023 | Resource Division | 27.82 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS | SM/17617 | New | Electrict quotation bill for TW-I of Golegram pwss (Ref Consumar ID-204391663),Application No-2004886425,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra |  |  | BILL/02426/2024-2025 | C092442840754 | 27/09/2024 | 27/09/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
Total | [13 empty] | 1049.04 | 233.74 | 22.28