## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS | SM/17618 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 350 cum OHR (Intze type with solid raft) & Accommodate FHTC (2,170 Nos.) including 2 years operation & maintenance under JJM with allied work for Khaskendu Bagicha & its adjoining mouzas W/S scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000388/2023-2024 | 5062/MD | 26/10/2023 | 23/04/2024 | CIVCON CONSTRUCTION PVT. LTD. | 548.71 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS | SM/17618 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001949/2022-2023 | 832/W/MMD | 24/03/2023 | 20/09/2023 | ORIENTAL ENGINEERING CO. | 23.76 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS | SM/17618 | New | Material Requisition To Resource Division |  |  | RTOR000249/2023-2024 | 1580/MD | 15/05/2023 | 15/05/2023 | Resource Division | 25.74 | 0 | 0 | 0
Total | [13 empty] | 598.2 | 0 | 0