## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS | SM/17619 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 01/10/2026 | GOBINDA MAITY | 4353.07 | 119.29 | 2.74 | 45
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS | SM/17619 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NIJPAPAN AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001939/2022-2023 | 824/W/MMD | 24/03/2023 | 31/10/2025 | P.K.ENGINEERING | 22.65 | 15.64 | 69.04 | 45
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS | SM/17619 | New | Material Requisition To Resource Division |  |  | RTOR000247/2023-2024 | 1584/MD | 15/05/2023 | 15/05/2023 | Resource Division | 22.79 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS | SM/17619 | New | Electrict quotation bill for TW-I of Nijpapan pwss (Ref Consumar ID-204439149),Application No-2004955912,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra |  |  | BILL/03036/2024-2025 | C112429784294 | 25/11/2024 | 25/11/2024 | WBSEDCL | 7.13 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS | SM/17619 | New | Electrict quotation bill for TW-II of Nijpapan pwss (Ref Consumar ID-204439153),Application No-2004955897,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra |  |  | BILL/03037/2024-2025 | C112429781413 | 25/11/2024 | 25/11/2024 | WBSEDCL | 8.48 | 0 | 0 | 0
Total | [13 empty] | 4414.12 | 134.93 | 3.06