## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17620 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000211/2023-2024 | 2826/MD | 07/08/2023 | 28/04/2026 | GOBINDA MAITY | 1375.06 | 302.14 | 21.97 | 74
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17620 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002202/2022-2023 | 483/W/MMD | 20/03/2023 | 31/07/2025 | M/S. P.P.ELECTRICALS | 22.95 | 21.4 | 93.25 | 90
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17620 | New | Material Requisition To Resource Division |  |  | RTOR000288/2023-2024 | 4060/MD | 12/10/2023 | 12/10/2023 | Resource Division | 29.73 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17620 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 2108/MD | 08/07/2024 | 08/07/2024 | Resource Division | 6.49 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17620 | New | Electric quotation bill for Gobindapur pwss at pump house no-II (Consumar Id-204182972) |  |  | BILL/03326/2023-2024 | BP-2023-24-537 | 11/01/2024 | 11/01/2024 | WBSEDCL | 3 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17620 | New | Electrict quation bill for gobindapur pwss at pump house no-I (Consumar Id-204182978) |  |  | BILL/03325/2023-2024 | BP-2023-24-536 | 11/01/2024 | 11/01/2024 | WBSEDCL | 3.28 | 0 | 0 | 0
Total | [13 empty] | 1440.53 | 323.54 | 22.46