## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | KEDAR AND ITS ADJOINING MOUJAS PWSS | SM/17621 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 1286/MD | 28/04/2023 | 28/04/2023 | Resource Division | 45.86 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | KEDAR AND ITS ADJOINING MOUJAS PWSS | SM/17621 | New | ADDITIONAL QUOTATION FOR SHIFTING OF 11 KV LINE & DTR AT TW NO-I OF KEDAR PWSS.(APPLICATION NO-2004886654), REFERENCE ID-860319778, APPLICATION ID-100000125268, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC- KHAKURDA CCC, NAME OF BLOCK-DANTAN-II. |  |  | BILL/03673/2024-2025 |  | 18/12/2024 | 18/12/2024 | WBSEDCL | 2.05 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | KEDAR AND ITS ADJOINING MOUJAS PWSS | SM/17621 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF KEDAR PWSS. REF CONSUMER ID-204393521, APPLICATION NO-2004889559, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02460/2024-2025 | C102401978777 | 03/10/2024 | 03/10/2024 | WBSEDCL | 6.65 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | KEDAR AND ITS ADJOINING MOUJAS PWSS | SM/17621 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF KEDAR PWSS. REF CONSUMER ID-204391651, APPLICATION NO-2004886654, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02463/2024-2025 | C102401977236 | 03/10/2024 | 03/10/2024 | WBSEDCL | 3.31 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-II | Central Drilling | KEDAR AND ITS ADJOINING MOUJAS PWSS | SM/17621 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | KEDAR AND ITS ADJOINING MOUJAS PWSS | SM/17621 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 0 | 0 | 30
Total | [13 empty] | 39401.1 | 0 | 0