## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17622 | New | Material Requisition To Resource Division |  |  | RTOR000232/2023-2024 | 1511/MD | 12/05/2023 |  | Resource Division | 26.72 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17622 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MADHABPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001900/2022-2023 | 799/W/MMD | 24/03/2023 | 20/09/2023 | BHABANI PRASAD MANNA | 21.62 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17622 | New | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000208/2023-2024 | 2824/MD | 07/08/2023 | 04/03/2024 | MADE AND TRADE CO. | 1346.28 | 0 | 0 | 64
Total | [13 empty] | 1394.63 | 0 | 0