## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS | SM/17623 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAGUYAN AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002199/2022-2023 | 456/W/MMD | 20/03/2023 | 16/09/2023 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS | SM/17623 | New | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 1413 | 04/05/2023 | 04/05/2023 | Resource Division | 37.1 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS | SM/17623 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 250 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,745 Nos.) including 2 years operation & maintenance under JJM with allied work for Baguyan & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000246/2023-2024 | 3053/MD | 23/08/2023 | 27/12/2025 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 452.52 | 0 | 0 | 40
Total | [13 empty] | 512.5 | 0 | 0