## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17624 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001894/2022-2023 | 793/W/MMD | 24/03/2023 | 12/09/2025 | M/S B.M. ELECTRICAL | 21.56 | 13.57 | 62.94 | 40
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17624 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 150 cum OHR (Intze type with solid raft) & Accommodate FHTC (1014 Nos) including 2 years operation & maintenance under JJM with allied work for Shyampur & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000236/2023-2024 | 3039/MD | 22/08/2023 | 07/02/2026 | CREATION CONSTRUCTION | 272.66 | 90.45 | 33.17 | 70
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17624 | New | Material Requisition To Resource Division |  |  | RTOR000222/2023-2024 | 1513/MD | 12/05/2023 | 12/05/2023 | Resource Division | 28.97 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17624 | New | Electrict quotation bill for TW-I of Shyampur pwss (Ref Consumar ID-204391666),Application No-2004886437,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra |  |  | BILL/02425/2024-2025 | BP-2024-25-682 | 27/09/2024 | 27/09/2024 | WBSEDCL | 5.56 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/17624 | New | Electrict quotation bill for TW-II of Shyampur pwss (Ref Consumar ID-204491137),Application No-2005035406,Application Type-New Connection,Name of CCC-Lowada ccc, block-Debra |  |  | BILL/04213/2024-2025 | C032554707855 | 17/03/2025 | 17/03/2025 | WBSEDCL | 7.5 | 0 | 0 | 0
Total | [13 empty] | 336.24 | 104.02 | 30.94