## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/17949 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 200/MD | 16/01/2023 | 16/01/2023 | Resource Division | 1.26 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/17949 | Augmentation | QUOTATION FOR NEW POWER CONNECTION OF SHYAMSUNDAR [AUG.] WATER SUPPLY ASCHEME [ APPLICATION --2004480397 REFERENCE ID ----204122721 SABONG CCC, QUOTATION NO ---2004480397/QUOT/03 DATED 26/10/2023, SCHEME NAME --- SHYAMSUNDAR AUG. , SCHEME CODE ---SM/17949 , MB NO--3580 ] |  |  | BILL/02884/2023-2024 | BP-2023-24-343 | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.49 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/17949 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Shyamsundarpur Water Supply Scheme within Sabang Block under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000001/2023-2024 | 953/MD | 06/04/2023 | 09/07/2025 | CREATION CONSTRUCTION | 222.15 | 97.75 | 44 | 90
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/17949 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002200/2022-2023 | 458/W/MMD | 20/03/2023 | 16/09/2023 | S.B.ENTERPRISE | 10.91 | 10.01 | 91.7 | 100
Total | [13 empty] | 237.82 | 107.76 | 45.31