## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Central Drilling | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.03 | 0.06 | 11
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,23,486 Nos.) for 89 Nos. PWSS within GARBETA-I, GARBETA-III, SALBANI & GARBETA-II Block Pipe Water Supply Scheme under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II),JE RWS Sadar Sub-Division(Garbeta-III),JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000282/2023-2024 | 5091/MD | 30/10/2023 | 19/10/2026 | RMN INFRASTRUCTURES LIMITED | 34739.93 | 111.96 | 0.32 | 40
3 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 1271/MD | 28/04/2023 | 28/04/2023 | Resource Division | 21.29 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | New service connection charges for Saiyadpur pwss, t/w no. II |  |  | BILL/00074/2024-2025 | 48/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 7.54 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | New service connection charges for Saiyadpur pwss, t/w no.I |  |  | BILL/00075/2024-2025 | 49/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 8.15 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | Route survey & way leave permission along & across of National Highway under Saiyadpur PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000456/2024-2025 | 373/MD | 31/01/2025 | 21/02/2025 | DONA ASSOCIATES | 11.88 | 0 | 0 | 0
Total | [13 empty] | 56128.55 | 124.99 | 0.22