## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 1271/MD | 28/04/2023 | 28/04/2023 | Resource Division | 21.29 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | New service connection charges for Saiyadpur pwss, t/w no. II |  |  | BILL/00074/2024-2025 | 48/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 7.54 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | New service connection charges for Saiyadpur pwss, t/w no.I |  |  | BILL/00075/2024-2025 | 49/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 8.15 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SAIYADPUR AND ADJOINING MOUJAS PWSS | SM/17996 | New | Route survey & way leave permission along & across of National Highway under Saiyadpur PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000456/2024-2025 | 373/MD | 31/01/2025 | 21/02/2025 | DONA ASSOCIATES | 11.88 | 0 | 0 | 0
Total | [13 empty] | 48.86 | 0 | 0