## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 1299/MD | 28/04/2023 | 28/04/2023 | Resource Division | 72.43 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Electric quotation bill for tw no-I of Sashabedia PWSS . (Ref ID-204061143). |  |  | BILL/01763/2023-2024 | BP-2023-24-182 | 11/08/2023 | 11/08/2023 | WBSEDCL | 3.09 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Sinking of 4 (four) nos. 250 X 150 mm dia. X 180 mtr. Depth deep tube well by direct rotary method for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-VII] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000079/2023-2024 | 2426/MD | 13/07/2023 | 27/08/2023 | MIDNAPUR PIPE CONCERN | 34.6 | 0 | 0 | 80
4 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and FHTC work (440 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-III] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000102/2023-2024 | 2484/MD | 17/07/2023 | 15/09/2023 | MIDNAPUR PIPE CONCERN | 96.29 | 0 | 0 | 70
5 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Laying distribution of Pipe line and Accommodate FHTC (459 Nos.) work for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-V] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000006/2023-2024 | 975/MD | 10/04/2023 | 09/06/2023 | J.K. BUILDERS | 77.87 | 0 | 0 | 100
6 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | New Service connection charges. |  |  | BILL/01284/2023-2024 | 55/JMD | 08/02/2024 | 08/02/2024 | WBSEDCL | 5.67 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | New Service connection charges. |  |  | BILL/01285/2023-2024 | 56/JMD | 08/02/2024 | 08/02/2024 | WBSEDCL | 5.67 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | New Service connection charges. |  |  | BILL/01286/2023-2024 | 57/JMD | 08/02/2024 | 08/02/2024 | WBSEDCL | 3.49 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Garbeta-II | Central Drilling | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Laying distribution of Pipe line and Accommodate FHTC (440 Nos.) work for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-IV] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000123/2023-2024 | 2522/MD | 18/07/2023 | 27/02/2025 | S.N ENTERPRISE | 66.39 | 0 | 0 | 80
11 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Laying distribution of Pipe line, Rising main, Construction of Pump House, Boundary wall, FHTC work (360 Nos.) with 2 years operation & maintenance for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-II] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000194/2023-2024 | 2808/MD | 07/08/2023 | 05/05/2025 | CHANDAN ROY | 157.84 | 0 | 0 | 2
12 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and FHTC work (300 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-VI] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000234/2023-2024 | 3004/MD | 21/08/2023 | 06/12/2025 | A.K. SIKDAR | 118.98 | 0 | 0 | 70
13 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | SASHA BEDIA AND ADJOINING MOUJAS PWSS | SM/18001 | New | Construction and Commissioning of 450 Cum Capacity (Intze type with Pile) Over Headed Reservoir, Soil Investigation, Construction of Pump House, Boundary wall & accommodate FHTC (600 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-I] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000854/2023-2024 | 831/MD | 15/03/2024 | 06/03/2026 | SUNIL DULE | 183.79 | 0 | 0 | 30
Total | [13 empty] | 22165.87 | 0 | 0