## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 1302/MD | 28/04/2023 | 28/04/2023 | Resource Division | 20.4 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | New service connection charges for Saldahara pwss, t/w no. II |  |  | BILL/00076/2024-2025 | 50/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 7.59 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | New service connection charges for Saldahara pwss, t/w no.I |  |  | BILL/01371/2023-2024 | 34/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.32 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Salbani | Midnapore Mechanical | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SHAL DAHARA AND ADJOINING MOUJAS PWWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002208/2022-2023 | 619/W/MMD | 20/03/2023 | 01/09/2024 | SUJOY RANJAN BHOWMICK | 21.58 | 0 | 0 | 56
5 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | Route survey & way leave permission along & across of National Highway in Shaldahara PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division |  | ORD/000459/2024-2025 | 375/MD | 31/01/2025 | 21/02/2025 | DONA ASSOCIATES | 12.25 | 0 | 0 | 0
Total | [13 empty] | 65.14 | 0 | 0