## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Mechanical | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SHAL DAHARA AND ADJOINING MOUJAS PWWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002208/2022-2023 | 619/W/MMD | 20/03/2023 | 01/09/2024 | SUJOY RANJAN BHOWMICK | 21.58 | 14.72 | 68.2 | 56
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,23,486 Nos.) for 89 Nos. PWSS within GARBETA-I, GARBETA-III, SALBANI & GARBETA-II Block Pipe Water Supply Scheme under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II),JE RWS Sadar Sub-Division(Garbeta-III),JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000282/2023-2024 | 5091/MD | 30/10/2023 | 19/10/2026 | RMN INFRASTRUCTURES LIMITED | 34739.93 | 71.39 | 0.21 | 40
3 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 1302/MD | 28/04/2023 | 28/04/2023 | Resource Division | 20.4 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Salbani | Central Drilling | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000002/2024-2025 | 188/CDD | 17/05/2024 | 17/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 700.39 | 0 | 0 | 15
5 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | New service connection charges for Saldahara pwss, t/w no. II |  |  | BILL/00076/2024-2025 | 50/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 7.59 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | New service connection charges for Saldahara pwss, t/w no.I |  |  | BILL/01371/2023-2024 | 34/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.32 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | SM/18013 | New | Route survey & way leave permission along & across of National Highway in Shaldahara PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division |  | ORD/000459/2024-2025 | 375/MD | 31/01/2025 | 21/02/2025 | DONA ASSOCIATES | 12.25 | 0 | 0 | 0
Total | [13 empty] | 35505.47 | 86.1 | 0.24