## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-III | Midnapore Division | SHUKHNATOR AND ADJOINING MOUJAS PWSS | SM/18020 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1227/MD | 27/04/2023 | 27/04/2023 | Resource Division | 38.62 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | SHUKHNATOR AND ADJOINING MOUJAS PWSS | SM/18020 | New | Quotation for new service connection at Sukhnator T/W-I water supply scheme. |  |  | BILL/00069/2024-2025 | 43/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 14.15 | 0 | 0 | 0
Total | [13 empty] | 52.77 | 0 | 0