## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Sinking of 2 (Two) nos. 250 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Dhanyagachhi PWSS with in Chandrakona- II block under Midnapore Division, P.H.E Dte. [PART-F] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000004/2023-2024 | 973/MD | 10/04/2023 | 01/05/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.67 | 15.81 | 76.5 | 100
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Laying of Distribution pipe line for Dhanyagachhi & its adjoing mouza Water Supply Scheme under Chandrakona-II block within Midnapore Division, PHE Dte. [PART-D] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000022/2023-2024 | 1024/MD | 12/04/2023 | 12/05/2023 | R. CONSTRUCTION | 31.96 | 31.54 | 98.69 | 100
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 203/MD | 16/01/2023 | 16/01/2023 | Resource Division | 32.91 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | New service connection |  |  | BILL/00626/2023-2024 | 9/JMD | 11/10/2023 | 11/10/2023 | WBSEDCL | 7.31 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | New service connection |  |  | BILL/00625/2023-2024 | 8/JMD | 11/10/2023 | 11/10/2023 | WBSEDCL | 11.96 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Laying of Distribution pipe line for Dhanyagachhi & its adjoing mouza Water Supply Scheme under Chandrakona-II block within Midnapore Division, PHE Dte. [PART-E] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000023/2023-2024 | 1025/MD | 12/04/2023 | 12/05/2023 | A R ENTERPRISE | 20.19 | 16.86 | 83.5 | 90
7 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for Dhanyagachhi PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE. Dte. [PART-C] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000003/2023-2024 | 972/MD | 10/04/2023 | 25/05/2023 | WATER LINK | 64.63 | 59.32 | 91.79 | 85
8 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for Dhanyagachhi PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE. Dte. [PART-A] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000034/2023-2024 | 1142/MD | 25/04/2023 | 22/10/2023 | SUJATA CONSTRUCTION | 262.98 | 40.5 | 15.4 | 30
9 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. |  |  | ORD/002036/2022-2023 | 944/W/MMD | 28/03/2023 | 24/09/2023 | DEBJYOTI BASU | 25.25 | 24.62 | 97.48 | 100
10 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 3332/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.85 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18027 | New | Laying distribution pipe line, Construction of Pump house & Boundary wall in 2nd tube well site for Dhanyagachhi PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE. Dte. [PART-B] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000002/2023-2024 | 971/MD | 10/04/2023 | 01/01/2025 | PULLOCK KUMAR GHOSH | 59.41 | 46 | 77.42 | 75
Total | [13 empty] | 548.1 | 234.65 | 42.81