## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18028 | New | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,649 Nos.) under JJM with allied work for Dhunrabila PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000038/2023-2024 | 1026/MD | 12/04/2023 | 27/03/2026 | SATYABRATA CHAKRABORTY | 566.32 | 178.37 | 31.5 | 50
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18028 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. |  |  | ORD/002206/2022-2023 | 587/W/MMD | 20/03/2023 | 16/09/2023 | M/S NABIN GOPAL SENGUPTA | 25.24 | 24.78 | 98.17 | 100
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18028 | New | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 111/MD | 10/01/2023 | 10/01/2023 | Resource Division | 32.36 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18028 | New | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 1456/MD | 08/05/2023 | 08/05/2023 | Resource Division | 10.16 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18028 | New | New Service connection charges. |  |  | BILL/01405/2023-2024 | 69/JMD | 13/03/2024 | 13/03/2024 | WBSEDCL | 5.25 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18028 | New | New Service connection charges. |  |  | BILL/01283/2023-2024 | 54/JMD | 07/02/2024 | 07/02/2024 | WBSEDCL | 4.29 | 0 | 0 | 0
Total | [13 empty] | 643.62 | 203.15 | 31.56