## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18171 | New | Material Requisition To Resource Division |  |  | RTOR000284/2023-2024 | 4058/MD | 12/10/2023 | 12/10/2023 | Resource Division | 40.25 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18171 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 3327/MD | 25/11/2024 | 25/11/2024 | Resource Division | 8.98 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18171 | New | New Service connection charges. |  |  | BILL/01362/2023-2024 | 25/JMD | 06/03/2024 | 06/03/2024 | WBSEDCL | 7.47 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18171 | New | Quotation for Bagchori T/W - I water supply scheme. |  |  | BILL/01366/2023-2024 | 29/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 7.47 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18171 | New | Sinking of Tube wells, Construction of 450 CuM Capacity R.C.C Over Head Reservoirs (Over Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6507) for Bagchhari & Mangrul Pipe W/S Scheme including Two years O&M within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000209/2023-2024 | 2825/MD | 07/08/2023 | 28/09/2025 | GOBINDA MAITY | 1766.48 | 291.01 | 16.47 | 70
6 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18171 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BAGCHHARI Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. |  |  | ORD/000751/2023-2024 | 2281/W/MMD | 29/08/2023 | 01/02/2025 | DEBJYOTI BASU | 30.12 | 15.79 | 52.41 | 100
Total | [13 empty] | 1860.78 | 306.8 | 16.49