## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18172 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Basanchhara & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000098/2022-2023 | 1018/MD | 27/05/2022 | 16/06/2022 | SIRCON ENGINEERING SERVICES | 6 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18172 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,044 Nos.) under JJM including Two years O&M with allied work for Basanchhara PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000273/2023-2024 | 3260/MD | 12/09/2023 | 07/03/2026 | M/S. D.K.H.CONSTRUCTION | 776.36 | 384.14 | 49.48 | 70
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18172 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BASANCHHARA Water supply scheme, Chandrakona -II block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. |  |  | ORD/000754/2023-2024 | 2284/W/MMD | 29/08/2023 | 25/02/2024 | RSA ENTERPRISE | 30.18 | 24.19 | 80.16 | 100
4 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18172 | New | Material Requisition To Resource Division |  |  | RTOR000289/2023-2024 | 4061/MD | 12/10/2023 | 12/10/2023 | Resource Division | 47.34 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18172 | New | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 3334/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.6 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18172 | New | New Service connection charges. |  |  | BILL/01282/2023-2024 | 53/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 3.82 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18172 | New | New Service connection charges. |  |  | BILL/01359/2023-2024 | 23/JMD | 04/03/2024 | 04/03/2024 | WBSEDCL | 9.72 | 0 | 0 | 0
Total | [13 empty] | 884.02 | 408.33 | 46.19