## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18173 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Lakshipur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000089/2022-2023 | 665/MD | 08/04/2022 | 28/04/2022 | SIRCON ENGINEERING SERVICES | 4.89 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18173 | New | Material Requisition To Resource Division |  |  | RTOR000283/2023-2024 | 4055/MD | 12/10/2023 | 12/10/2023 | Resource Division | 42.67 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18173 | New | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 3328/MD | 25/11/2024 | 25/11/2024 | Resource Division | 9.41 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18173 | New | New service connection |  |  | BILL/01312/2023-2024 | 83/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18173 | New | New Service connection charges. |  |  | BILL/01137/2023-2024 | 22/JMD | 11/01/2024 | 11/01/2024 | WBSEDCL | 2.79 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18173 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,522 Nos.) under JJM including Two years O&M with allied work for Lakshipur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000264/2023-2024 | 3238/MD | 11/09/2023 | 27/03/2026 | UNIQUE AGENCY | 619.92 | 0 | 0 | 72
7 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18173 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at LAKSHIPUR Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. |  |  | ORD/000752/2023-2024 | 2282/W/MMD | 29/08/2023 | 30/06/2024 | SUJOY RANJAN BHOWMICK | 30.18 | 0 | 0 | 95
Total | [13 empty] | 714.04 | 0 | 0