## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/18184 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. |  |  | ORD/000007/2023-2024 | 1123/W/MMD | 12/04/2023 | 01/07/2025 | R.S. ENTERPRISE | 25.24 | 11.81 | 46.78 | 60
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/18184 | New | Sinking of Tube Well ,Laying distribution pipe line, Providing FHTC (6843 Nos),Construction of Pump House , Boundary Wall soil investigation , RCC OHR (450 cum &400 Cum Capacity respectively) with allied work for Khandanga PWSS & Piardanga PWSS & its adjoining mouzas W/S scheme in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II),JE1 Ghatal Sub-division | ORD/000070/2023-2024 | 2417/MD | 13/07/2023 | 30/05/2026 | AMAL DUTTA ROY | 1448.03 | 0 | 0 | 40
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/18184 | New | Material Requisition To Resource Division |  |  | RTOR000240/2023-2024 | 1524/MD | 12/05/2023 | 12/05/2023 | Resource Division | 53.67 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/18184 | New | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components installed at Pump House no. 1 of Piyardanga W/S Scheme in the district of Paschim Medinipur under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000511/2024-2025 | 6638/JMD | 22/08/2024 | 22/08/2025 | R S ENTERPRISE | 3.54 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/18184 | New | New Service connection charges. |  |  | BILL/01472/2023-2024 | 81/JMD | 20/03/2024 | 20/03/2024 | WBSEDCL | 6.88 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/18184 | New | New Service connection charges. |  |  | BILL/01330/2023-2024 | 97/JMD | 22/02/2024 | 22/02/2024 | WBSEDCL | 4.13 | 0 | 0 | 0
Total | [13 empty] | 1541.48 | 11.81 | 0.77