## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Mechanical | KADABANI AND ADJOINING MOUJAS PWSS | SM/18188 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KADABANI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. |  |  | ORD/000006/2023-2024 | 1122/W/MMD | 12/04/2023 | 09/10/2023 | ABHIJIT MUKHERJEE | 21.56 | 13.58 | 62.99 | 40
2 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | KADABANI AND ADJOINING MOUJAS PWSS | SM/18188 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,23,486 Nos.) for 89 Nos. PWSS within GARBETA-I, GARBETA-III, SALBANI & GARBETA-II Block Pipe Water Supply Scheme under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II),JE RWS Sadar Sub-Division(Garbeta-III),JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000282/2023-2024 | 5091/MD | 30/10/2023 | 19/10/2026 | RMN INFRASTRUCTURES LIMITED | 34739.93 | 89.57 | 0.26 | 40
3 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | KADABANI AND ADJOINING MOUJAS PWSS | SM/18188 | New | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 1155/MD | 25/04/2023 | 25/04/2023 | Resource Division | 18.05 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | KADABANI AND ADJOINING MOUJAS PWSS | SM/18188 | New | NEW SERVICE CONNECTION CHARGES AT KADABONI TW-I WATER SUPPLY SCHEME |  |  | BILL/00569/2024-2025 | 248/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 7.78 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | KADABANI AND ADJOINING MOUJAS PWSS | SM/18188 | New | NEW SERVICE CONNECTION CHARGES AT KADABANI T/W-II WATER SUPPLY SCHEME |  |  | BILL/01613/2024-2025 | 464/JMD | 21/01/2025 | 21/01/2025 | WBSEDCL | 9.24 | 0 | 0 | 0
Total | [13 empty] | 34796.55 | 103.15 | 0.3