## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | KADABANI AND ADJOINING MOUJAS PWSS | SM/18188 | New | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 1155/MD | 25/04/2023 | 25/04/2023 | Resource Division | 18.05 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Mechanical | KADABANI AND ADJOINING MOUJAS PWSS | SM/18188 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KADABANI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. |  |  | ORD/000006/2023-2024 | 1122/W/MMD | 12/04/2023 | 09/10/2023 | ABHIJIT MUKHERJEE | 21.56 | 13.58 | 62.99 | 40
3 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | KADABANI AND ADJOINING MOUJAS PWSS | SM/18188 | New | NEW SERVICE CONNECTION CHARGES AT KADABONI TW-I WATER SUPPLY SCHEME |  |  | BILL/00569/2024-2025 | 248/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 7.78 | 0 | 0 | 0
Total | [13 empty] | 47.38 | 13.58 | 28.65