## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/18191 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002207/2022-2023 | 617/W/MMD | 20/03/2023 | 16/09/2023 | JAGANNATH ENTERPRISE | 21.58 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/18191 | Augmentation | Laying distribution pipe under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000139/2023-2024 | 2623/MD | 24/07/2023 | 07/09/2023 | M/S. BLUE BIRD | 21.94 | 15.85 | 72.21 | 71
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/18191 | Augmentation | Preparation of D.P.R {Consultancy work} in connection with the Functional House Hold Tap connection for Rejuvenation /Augmentation of existing AMRAKUCHI PWSS within Keshpur Block under Midnapore Division PHE Dte. (SL No-01) | AE Sadar Sub-division |  | ORD/000296/2022-2023 | 461/AE/MSSD | 05/08/2022 | 20/08/2022 | ROY DESIGN & INFRASTRUCTURE | 2.15 | 2.14 | 99.68 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/18191 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000129/2022-2023 | 377/MD | 03/02/2023 | 03/02/2023 | Resource Division | 27.13 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/18191 | Augmentation | Sinking of Tube well, Laying distribution pipe line & accommodate FHTC (118 Nos.) including 2 years O&M under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur),JE2 Sadar Sub-division | ORD/000040/2023-2024 | 1356/MD | 02/05/2023 | 01/07/2023 | PULLOCK KUMAR GHOSH | 54.56 | 30.64 | 56.17 | 85
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/18191 | Augmentation | ELECTRIC QUOTATION BILL FOR ADDITIONAL TW NO-III of AMRAKUCHI PWSS. REF CONSUMER ID-204269829, APPLICATION NO-2004675304, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00317/2024-2025 | BP-2024-25-73 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.4 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/18191 | Augmentation | Sinking of Tube well, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 100 CuM OHR (Torch type with solid raft) & Accommodate FHTC (250 Nos.) under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000110/2024-2025 | 3043/MD | 25/09/2024 | 19/03/2026 | WATER LINK | 114.3 | 8 | 7 | 30
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/18191 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000005/2023-2024 | 1121/W/MMD | 12/04/2023 | 08/03/2025 | S.S.GHORAI | 22.89 | 12.33 | 53.86 | 20
Total | [13 empty] | 267.95 | 68.95 | 25.73