## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | Sinking of 1 (One) No. 200 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. [Part-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000143/2023-2024 | 2627/MD | 24/07/2023 | 03/08/2023 | GOPAL RANA | 6.01 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | Sinking of 2 (Two) Nos. 150 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000142/2023-2024 | 2626/MD | 24/07/2023 | 14/08/2023 | MIDNAPUR PIPE CONCERN | 11.81 | 9.59 | 81.24 | 100
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 1366/MD | 02/05/2023 | 02/05/2023 | Resource Division | 22.98 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | QUOTATION FOR NEW POWER CONNECTION OF KESHURIA [ ZONE-II/ T W -I] WATER SUPPLY ASCHEME [ APPLICATION --2004479640, REFERENCE ID ----204122245, NIMPURA CCC, QUOTATION NO ---2004479640/QUOT/03 DATED 26/10/2023, SCHEME NAME --- KESHURIA [ ZONE-II/ TW -I] . , SCHEME CODE ---SM/18192 , MB NO--3580 ] |  |  | BILL/02916/2023-2024 | BP-2023-24-345 | 10/11/2023 | 10/11/2023 | WBSEDCL | 0.51 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | QUOTATION FOR NEW POWER CONNECTION OF KESHURIA [ ZONE-II/ T W -II] WATER SUPPLY ASCHEME [ APPLICATION --2004479660, REFERENCE ID ----204122246, NIMPURA CCC, QUOTATION NO ---2004479660/QUOT/03 DATED 26/10/2023, SCHEME NAME --- KESHURIA [ ZONE-II/ TW -II] . , SCHEME CODE ---SM/18192 , MB NO--3580 ] |  |  | BILL/02917/2023-2024 | BP-2023-24-346 | 10/11/2023 | 10/11/2023 | WBSEDCL | 4.04 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | Sinking of 1 (One) No. 200 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. [Part-I] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000106/2023-2024 | 2488/MD | 17/07/2023 | 27/07/2023 | MAHALAKSHMI ENTERPRISE | 5.88 | 5.07 | 86.24 | 100
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | QUOTATION MONEY FOR KESHURIA WATER SUPPLY SCHEME, ZONE- I , T W NO I , [ DARKHOLA ] , JJM WORKS, SCHEME CODE SM/18192, APPLICATION NO 2004890131, REFERENCE ID 204393531, NIMPURA CCC, WBSEDCL |  |  | BILL/02979/2024-2025 | C112417260038 | 12/11/2024 | 12/11/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER Kharagpur - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000038/2023-2024 | 1187/W/MMD | 25/04/2023 | 22/10/2023 | A G ENTERPRISE | 40.67 | 20.73 | 50.98 | 40
9 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | Construction of 250 Cum capacity R.C.C. Over Head Reservoirs including Sub-Soil Investigation work with Laying of distribution system, Pump Houses, Boundary Walls & providing Functional Household Tap Connection (1258 Nos.) including 02 (Two) years O & M for KESHURIA (ZONE-I,II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000205/2025-2026 | 1778/MD | 08/09/2025 | 07/03/2026 | CHAKRBORTTI ENTERPRISE | 334.01 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18192 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 10/09/2024 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
Total | [13 empty] | 441.49 | 35.4 | 8.02