## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | NARMA AND ADJOINING MOUJAS PWSS | SM/18229 | New | Material Requisition To Resource Division |  |  | RTOR000237/2023-2024 | 1531/MD | 12/05/2023 | 12/05/2023 | Resource Division | 73.62 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | NARMA AND ADJOINING MOUJAS PWSS | SM/18229 | New | Quotation for new power connection at Narma PWSS T/W no - II of Narayangarh block Application no - 2004754830 , Ref ID - 204323480 |  |  | BILL/01303/2024-2025 | BP-2024-25-338 | 25/06/2024 | 25/06/2024 | WBSEDCL | 8.18 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | NARMA AND ADJOINING MOUJAS PWSS | SM/18229 | New | Quotation for new power connection at Narma PWSS P/H- I , application no - 2004609088 , Ref id - 204223723 |  |  | BILL/04199/2023-2024 | BP-2023-24-782 | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.45 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | NARMA AND ADJOINING MOUJAS PWSS | SM/18229 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 20.73 | 0.1 | 11
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | NARMA AND ADJOINING MOUJAS PWSS | SM/18229 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE1 Kharagpur Sub-division | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 13/12/2025 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 239.24 | 2.82 | 41
Total | [13 empty] | 29923.33 | 259.97 | 0.87