## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Laying distribution system & Accommodate FHTC (300 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Ghatal Sub-division |  | ORD/000086/2023-2024 | 2433/MD | 13/07/2023 | 11/09/2023 | DEV KUMAR ADAK | 44.86 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Laying distribution system & Accommodate FHTC (200 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Ghatal Sub-division |  | ORD/000087/2023-2024 | 2434/MD | 13/07/2023 | 11/09/2023 | M/S JITEN BANARJEE | 37.78 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Laying distribution system & Accommodate FHTC (200 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Ghatal Sub-division |  | ORD/000088/2023-2024 | 2435/MD | 13/07/2023 | 27/08/2023 | SUBHASIS DOLAI | 28.79 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Laying distribution system with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-G] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000133/2023-2024 | 2592/MD | 21/07/2023 | 20/08/2023 | LOWADA HI-TECHTONIC ENGINEER,S CO. OP. SOCIETY LTD. | 18.92 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 77/MD | 09/01/2023 | 09/01/2023 | Resource Division | 38.5 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. |  |  | ORD/000212/2023-2024 | 1494/W/MMD | 22/06/2023 | 19/12/2023 | DEBJYOTI BASU | 27.38 | 0 | 0 | 80
7 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Laying distribution system & Accommodate FHTC (500 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000135/2023-2024 | 2594/MD | 21/07/2023 | 19/09/2023 | R. CONSTRUCTION | 92.24 | 0 | 0 | 40
8 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Krishnapur PWSS within Chandrakona-II block under Midnapore Division, P.H.E Dte. [PART-I] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000076/2023-2024 | 2423/MD | 13/07/2023 | 03/08/2023 | SAJAL JANA | 22.7 | 0 | 0 | 50
9 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 3333/MD | 25/11/2024 | 25/11/2024 | Resource Division | 21.7 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Quotation for new service connection at Krishnapur T/W-II water supply scheme. |  |  | BILL/00880/2024-2025 | 308/JMD | 14/08/2024 | 14/08/2024 | WBSEDCL | 3.11 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | New Service connection charges. |  |  | BILL/01363/2023-2024 | 26/JMD | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.38 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Quotation for Krishnapur T/W - I water supply scheme. |  |  | BILL/01367/2023-2024 | 30/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.38 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Laying distribution system & Accommodate FHTC (300 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-H] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000089/2023-2024 | 2436/MD | 13/07/2023 | 01/02/2026 | DEVJYOTI BERA | 58.24 | 0 | 0 | 45
14 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | SM/18233 | New | Laying distribution pipe line, Rising main & Accommodate FHTC (500 Nos.) including 2 years operation & maintenance with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000195/2023-2024 | 2809/MD | 07/08/2023 | 27/10/2025 | M/S. D.K.H.CONSTRUCTION | 149.24 | 0 | 0 | 35
Total | [13 empty] | 550.21 | 0 | 0