## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18235 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum OHR each (Intze type with pile foundation) & Accommodate FHTC (6283 Nos.) under JJM with allied work for Purshuri & Ramkrishnapur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000075/2023-2024 | 2422/MD | 13/07/2023 | 27/03/2026 | GOBINDA MAITY | 1504.9 | 308.48 | 20.5 | 60
2 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18235 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. |  |  | ORD/000206/2023-2024 | 1491/W/MMD | 22/06/2023 | 06/06/2025 | SUJOY RANJAN BHOWMICK | 23.69 | 14.1 | 59.52 | 100
3 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18235 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 78/MD | 09/01/2023 | 09/01/2023 | Resource Division | 32.78 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18235 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 3329/MD | 25/11/2024 | 25/11/2024 | Resource Division | 21.66 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18235 | New | New Service connection charges. |  |  | BILL/01478/2023-2024 | 83/JMD | 21/03/2024 | 21/03/2024 | WBSEDCL | 3.28 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18235 | New | Quotation for new service connection at RAMKRISHNAPUR T/W-II water supply scheme. |  |  | BILL/00286/2024-2025 | 124/JMD | 20/05/2024 | 20/05/2024 | WBSEDCL | 3.17 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18235 | New | SHIFTING OF 11 KV HTOH LINE HATPUKUR FEEDER FOR CONSTRUCTION OF RAMKRISHNAPUR T/W-I P.H. |  |  | BILL/00517/2024-2025 | 234/JMD | 09/07/2024 | 09/07/2024 | WBSEDCL | 2.52 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18235 | New | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000380/2024-2025 | 55/MD | 07/01/2025 | 14/12/2025 | GOBINDA MAITY | 79.62 | 0 | 0 | 60
Total | [13 empty] | 1671.62 | 322.58 | 19.3