## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18236 | New | Laying distribution pipe line, Pump House, Boundary wall under JJM with allied work for Bandipur PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000085/2023-2024 | 2432/MD | 13/07/2023 | 11/09/2023 | GOUTAM RAY | 77.39 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18236 | New | Construction of Pump House, Boundary wall , Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for Bandipur PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000266/2023-2024 | 3240/MD | 11/09/2023 | 09/03/2024 | CHAKRABORTTI ENTERPRISE | 260.37 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18236 | New | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 202/MD | 16/01/2023 | 16/01/2023 | Resource Division | 37.26 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18236 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. |  |  | ORD/000214/2023-2024 | 1495/W/MMD | 22/06/2023 | 19/12/2023 | DEBJYOTI BASU | 25.25 | 0 | 0 | 80
5 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18236 | New | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 3331/MD | 25/11/2024 | 25/11/2024 | Resource Division | 15.69 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18236 | New | New service connection for Bandipur W/S Scheme |  |  | BILL/01039/2024-2025 | 379/JMD | 30/09/2024 | 30/09/2024 | WBSEDCL | 6.77 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18236 | New | Laying distribution pipe line, Accommodate FHTC, Laying Rising main, Operation & Maintenance under JJM with allied work for Bandipur PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000285/2023-2024 | 3902/MD | 27/09/2023 | 28/10/2025 | M/S. D.K.H.CONSTRUCTION | 327.58 | 0 | 0 | 30
8 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | SM/18236 | New | Sinking of 2 (Two) nos. 250 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Bandipur PWSS with in Chandrakona- II block under Midnapore Division, P.H.E Dte. [PART-D] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000077/2023-2024 | 2424/MD | 13/07/2023 | 11/12/2024 | MR GOUTAM GHOSH, | 20.39 | 0 | 0 | 100
Total | [13 empty] | 770.71 | 0 | 0