## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Regular Upkeep of Drinking Water Testing Laboratory in Paschim Medinipur Under Midnapore Division, PHE dte. Related to Water Quality Monitoring and Surveillance Support Activities under Jal Jeevan Mission. | SM/18277 | Support-WQMSP | Repairing and Renovation work of an existing damaged PHE Dte. Laboratories building in connection with different 08 (Eight) Nos. Sub-District Water Testing Laboratories under Midnapore Division, PHE Dte. of Paschim Medinipur District. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),JE RWS Kharagpur Sub-Division( Sabang),JE RWS Midnapur Sub-Division( Dantan-I),JE1 Sadar Sub-division,JE2 Ghatal Sub-division,JE2 Kharagpur Sub Division,JE2 Sadar Sub-division,JE3 Kharagpur Sub-division | ORD/000333/2024-2025 | 3576/MD | 06/12/2024 | 31/03/2026 | D M CONSTRUCTION | 69.35 | 0 | 0 | 75
Total | [13 empty] | 69.35 | 0 | 0