## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 100 (Intze type Raft Foundation) & Accommodate FHTC (709 Nos.) including 2 years O&M under JJM with allied work for Chandipur (Zone-I) & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000287/2023-2024 | 3904/MD | 27/09/2023 | 25/03/2024 | KISHORE GHOSH | 219.55 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,212 Nos.) including 2 yrs. O & M under JJM with allied work for Gurehara & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | ORD/000447/2023-2024 | 5258/MD | 21/11/2023 | 20/01/2024 | SUNIL DULE | 119.03 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,039 Nos.) including 2 yrs. O & M under JJM with allied work for Garhberia & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | ORD/000444/2023-2024 | 5257/MD | 21/11/2023 | 20/01/2024 | CREATION CONSTRUCTION | 94.26 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,257 Nos.) including 2 yrs. O & M under JJM with allied work for Pathaisol & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | ORD/000755/2023-2024 | 218/MD | 31/01/2024 | 31/03/2024 | ASIS KUMAR SARANGI | 104.62 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 Cum OHR (Intze type Pile Foundation) & Accommodate FHTC (3,719 Nos.) including Two years O&M under JJM with allied work for Juarhati & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000773/2023-2024 | 438/MD | 20/02/2024 | 18/08/2024 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 575.05 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,164 Nos.) including 2 yrs. O & M under JJM with allied work for Banpura & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000637/2023-2024 | 141/MD | 18/01/2024 | 18/03/2024 | MIDNAPUR PIPE CONCERN | 96.72 | 0 | 0 | 10
7 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Construction of 250 (Intze type Raft Foundation) & Accommodate FHTC (2,237 Nos.) including Two years O&M under JJM with allied work for Panchkuri & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000226/2023-2024 | 2926/MD | 16/08/2023 | 12/02/2024 | M/S. CARE | 462.61 | 0 | 0 | 10
8 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction of Boundary wall, Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 cum and staging height 20 mtr & Accommodate FHTC (400 Nos.) under JJM with allied work for Mahadevchak & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000815/2023-2024 | 649/MD | 07/03/2024 | 03/09/2024 | SUBRATA DAS | 88.57 | 0 | 0 | 15
9 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Rising Main & Accommodate FHTC (618 Nos.) including 2 years O&M under JJM with allied work for Hatihalka & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000288/2023-2024 | 3905/MD | 27/09/2023 | 26/11/2023 | DIPAK KUMAR BAKLY | 61.27 | 0 | 0 | 60
10 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Boundary wall & Accommodate FHTC (500 Nos.) including 2 years O&M under JJM with allied work for Sholkamari & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000217/2023-2024 | 2870/MD | 10/08/2023 | 24/10/2023 | MIDNAPUR PIPE CONCERN | 213.41 | 0 | 0 | 60
11 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House & Accommodate FHTC (304 Nos.) under JJM with allied work for Khangardihi & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000244/2023-2024 | 3099/MD | 25/08/2023 | 24/10/2023 | PULLOCK KUMAR GHOSH | 83.11 | 0 | 0 | 1
12 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Pump House, Boundary Wall & Accommodate FHTC (354 Nos.) under JJM with allied work for Barua & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000243/2023-2024 | 3098/MD | 25/08/2023 | 09/10/2023 | PULLOCK KUMAR GHOSH | 36.04 | 0 | 0 | 5
13 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction and commissioning of RCC Over Head Reservoir (Intez type with solid raft) of capacity 200 cum and staging height 20 mtr., Boundary wall & Accommodate FHTC (500 Nos.) under JJM with allied work for Shiromani & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division |  | ORD/000022/2024-2025 | 2052/MD | 02/07/2024 | 29/12/2024 | ADITYA MALLIK | 108.95 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction of Boundary wall, Soil investigation, Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr. & Accommodate FHTC (1,423 Nos.) under JJM with allied work for Sholkamari & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division |  | ORD/000037/2024-2025 | 2146/MD | 11/07/2024 | 07/01/2025 | DIPAK KUMAR BAKLY | 175.22 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction of Boundary wall, Soil investigation, Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 200 cum and staging height 20 mtr & Accommodate FHTC (800 Nos.) under JJM with allied work for Pachra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division |  | ORD/000039/2024-2025 | 2219/MD | 19/07/2024 | 15/01/2025 | ASHIM KUMAR DEY | 126.93 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary wall, & Accommodate FHTC (659 Nos.) including 2 years O&M under JJM with allied work for Pachra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000245/2023-2024 | 3100/MD | 25/08/2023 | 08/11/2023 | M/S. D.K.H.CONSTRUCTION | 280.51 | 0 | 0 | 40
17 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Construction of 300 Cum OHR (Intze type Raft Foundation) & Accommodate FHTC (2,400 Nos.) including Two years O&M under JJM with allied work for Pathra & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000265/2023-2024 | 3239/MD | 11/09/2023 | 09/03/2024 | M/S. CARE | 492.38 | 0 | 0 | 10
18 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary wall & Accommodate FHTC (576 Nos.) including 2 years O&M under JJM with allied work for Mahadevchak & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000218/2023-2024 | 2871/MD | 10/08/2023 | 09/10/2023 | MIDNAPUR PIPE CONCERN | 131.19 | 0 | 0 | 35
19 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipeline, Rising main, Pump House, Boundary Wall & Accommodate FHTC (546 Nos.) including 2 yrs. O & M under JJM with allied work for Shiromani & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000636/2023-2024 | 140/MD | 18/01/2024 | 17/04/2024 | MIDNAPUR PIPE CONCERN | 186.66 | 0 | 0 | 20
Total | [13 empty] | 3656.11 | 0 | 0