## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Construction of 250 (Intze type Raft Foundation) & Accommodate FHTC (2,237 Nos.) including Two years O&M under JJM with allied work for Panchkuri & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000226/2023-2024 | 2926/MD | 16/08/2023 | 12/02/2024 | M/S. CARE | 462.61 | 0 | 0 | 10
2 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Pump House, Boundary Wall & Accommodate FHTC (354 Nos.) under JJM with allied work for Barua & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000243/2023-2024 | 3098/MD | 25/08/2023 | 09/10/2023 | PULLOCK KUMAR GHOSH | 36.04 | 0 | 0 | 5
3 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 100 (Intze type Raft Foundation) & Accommodate FHTC (709 Nos.) including 2 years O&M under JJM with allied work for Chandipur (Zone-I) & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000287/2023-2024 | 3904/MD | 27/09/2023 | 25/03/2024 | KISHORE GHOSH | 219.55 | 0 | 0 | 15
4 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 Cum OHR (Intze type Pile Foundation) & Accommodate FHTC (3,719 Nos.) including Two years O&M under JJM with allied work for Juarhati & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000773/2023-2024 | 438/MD | 20/02/2024 | 09/02/2026 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 575.05 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction of Boundary Wall, Construction & Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr. & Accommodate FHTC (691 Nos.) including 2 years O&M under JJM with allied work for Bishra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division |  | ORD/000337/2024-2025 | 3580/MD | 06/12/2024 | 04/06/2025 | DEBASISH DOGRA | 134.93 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction of Boundary wall, Soil investigation, Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 200 cum and staging height 20 mtr & Accommodate FHTC (800 Nos.) under JJM with allied work for Pachra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division |  | ORD/000039/2024-2025 | 2219/MD | 19/07/2024 | 15/01/2025 | ASHIM KUMAR DEY | 126.93 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 100 (Intze type Raft Foundation) & Accommodate FHTC (473 Nos.) including 2 years O&M under JJM with allied work for Chandipur (Zone-II) & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division |  | ORD/000177/2024-2025 | 3160/MD | 04/10/2024 | 02/04/2025 | ASHIM KUMAR DEY | 191.82 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Boundary wall & Accommodate FHTC (500 Nos.) including 2 years O&M under JJM with allied work for Sholkamari & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000217/2023-2024 | 2870/MD | 10/08/2023 | 23/01/2026 | MIDNAPUR PIPE CONCERN | 213.41 | 0 | 0 | 60
9 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary wall & Accommodate FHTC (576 Nos.) including 2 years O&M under JJM with allied work for Mahadevchak & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000218/2023-2024 | 2871/MD | 10/08/2023 | 10/01/2026 | MIDNAPUR PIPE CONCERN | 131.19 | 0 | 0 | 35
10 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House & Accommodate FHTC (304 Nos.) under JJM with allied work for Khangardihi & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000244/2023-2024 | 3099/MD | 25/08/2023 | 30/07/2025 | PULLOCK KUMAR GHOSH | 83.11 | 0 | 0 | 25
11 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Construction of 300 Cum OHR (Intze type Raft Foundation) & Accommodate FHTC (2,400 Nos.) including Two years O&M under JJM with allied work for Pathra & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000265/2023-2024 | 3239/MD | 11/09/2023 | 22/02/2025 | M/S. CARE | 492.38 | 0 | 0 | 10
12 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary wall, & Accommodate FHTC (659 Nos.) including 2 years O&M under JJM with allied work for Pachra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000245/2023-2024 | 3100/MD | 25/08/2023 | 08/08/2025 | M/S. D.K.H.CONSTRUCTION | 280.51 | 0 | 0 | 60
13 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,212 Nos.) including 2 yrs. O & M under JJM with allied work for Gurehara & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | ORD/000447/2023-2024 | 5258/MD | 21/11/2023 | 27/03/2026 | SUNIL DULE | 119.03 | 0 | 0 | 60
14 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,039 Nos.) including 2 yrs. O & M under JJM with allied work for Garhberia & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | ORD/000444/2023-2024 | 5257/MD | 21/11/2023 | 15/01/2025 | CREATION CONSTRUCTION | 94.26 | 0 | 0 | 40
15 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,164 Nos.) including 2 yrs. O & M under JJM with allied work for Banpura & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000637/2023-2024 | 141/MD | 18/01/2024 | 09/02/2026 | MIDNAPUR PIPE CONCERN | 96.72 | 0 | 0 | 10
16 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Laying distribution pipeline, Rising main, Pump House, Boundary Wall & Accommodate FHTC (546 Nos.) including 2 yrs. O & M under JJM with allied work for Shiromani & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000636/2023-2024 | 140/MD | 18/01/2024 | 08/02/2026 | MIDNAPUR PIPE CONCERN | 186.66 | 0 | 0 | 20
17 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying rising main, Pump House & Accommodate FHTC (1,257 Nos.) including 2 yrs. O & M under JJM with allied work for Pathaisol & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | ORD/000755/2023-2024 | 218/MD | 31/01/2024 | 09/09/2025 | ASIS KUMAR SARANGI | 104.62 | 0 | 0 | 95
18 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction of Boundary wall, Soil investigation, Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 cum and staging height 20 mtr. & Accommodate FHTC (1,000 Nos.) including 2 years O&M under JJM with allied work for Khangardihi & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000111/2024-2025 | 3044/MD | 25/09/2024 | 19/03/2026 | WATER LINK | 139.11 | 0 | 0 | 0
19 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Laying additional distribution pipeline, Land development at 1st Tube well cum Head work site & Accommodate FHTC (1,797 Nos.) including all allied works for Hatihalka PWSS within Midnapore Sadar block under Midnapore Division, PHE Dte. [Mid-Term Plan under Master Plan] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000309/2024-2025 | 3403/MD | 25/11/2024 | 18/02/2026 | UTTAM KUMAR DAS | 84.05 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction of Boundary wall, Soil investigation, Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr. & Accommodate FHTC (1,423 Nos.) under JJM with allied work for Sholkamari & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000037/2024-2025 | 2146/MD | 11/07/2024 | 02/01/2026 | DIPAK KUMAR BAKLY | 175.22 | 0 | 0 | 5
21 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction and commissioning of RCC Over Head Reservoir (Intez type with solid raft) of capacity 200 cum and staging height 20 mtr., Boundary wall & Accommodate FHTC (500 Nos.) under JJM with allied work for Shiromani & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000022/2024-2025 | 2052/MD | 02/07/2024 | 27/06/2025 | ADITYA MALLIK | 108.95 | 0 | 0 | 15
22 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr. as per approved drawing (No:- PC-I/OHR /10/15/2012) with allied works for Barua & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-C] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000336/2024-2025 | 3579/MD | 06/12/2024 | 01/12/2025 | GOUTAM PARIA | 71.28 | 0 | 0 | 0
23 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Accommodate FHTC (801 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM for Banpura PWSS within Midnapore Sadar Dev. Block under Midnapore Division in Paschim Medinipur district. [Mid-Term Plan under Master Plan] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000047/2025-2026 | 1067/MD | 02/05/2025 | 24/02/2026 | MIDNAPUR PIPE CONCERN | 30.79 | 0 | 0 | 0
24 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Construction and commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 250 CuM & staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/10/2012) with allied works for Banpura & its adjoining mouzas water supply scheme within Midnapore Sadar Block including supply of all labour & materials under Midnapore Division, PHE Dte. (Mid- Term Plan under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000203/2025-2026 | 1777/MD | 08/09/2025 | 07/03/2026 | M/S RAJKUMAR KHAN | 81.1 | 0 | 0 | 0
25 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | SM/18486 | Retrofitting | Sinking of Tube well, Rising Main & Accommodate FHTC (618 Nos.) including 2 years O&M under JJM with allied work for Hatihalka & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000288/2023-2024 | 3905/MD | 27/09/2023 | 01/11/2025 | DIPAK KUMAR BAKLY | 61.27 | 0 | 0 | 60
Total | [13 empty] | 4300.62 | 0 | 0