## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TORIA PIPED WATER SUPPLY SCHEME | SM/18494 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TORIA PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000362/2023-2024 | 1690/W/MMD | 04/08/2023 | 31/01/2024 | UTTAM KUMAR CHATTERJEE | 25.25 | 17.54 | 69.49 | 30
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | TORIA PIPED WATER SUPPLY SCHEME | SM/18494 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,702 nos.) under JJM with allied work for Torai PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000254/2023-2024 | 3149/MD | 29/08/2023 | 14/02/2026 | BANERJEE CONSTRUCTION | 869.66 | 293.49 | 33.75 | 55
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | TORIA PIPED WATER SUPPLY SCHEME | SM/18494 | New | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 110/MD | 10/01/2023 | 10/01/2023 | Resource Division | 15.28 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | TORIA PIPED WATER SUPPLY SCHEME | SM/18494 | New | Material Requisition To Resource Division |  |  | RTOR000048/2024-2025 | 3368/MD | 25/11/2024 | 25/11/2024 | Resource Division | 16.64 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TORIA PIPED WATER SUPPLY SCHEME | SM/18494 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of TORIA PWSS. REF CONSUMER ID-204248200, APPLICATION NO-2004645189, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/04584/2023-2024 | BP-2023-24-893 | 22/03/2024 | 22/03/2024 | WBSEDCL | 7.19 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TORIA PIPED WATER SUPPLY SCHEME | SM/18494 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF TORIA PWSS. REF CONSUMER ID-204370272, APPLICATION NO-2004843239 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESPUR |  |  | BILL/01875/2024-2025 | C082421721033 | 16/08/2024 | 16/08/2024 | WBSEDCL | 5.29 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | TORIA PIPED WATER SUPPLY SCHEME | SM/18494 | New | Laying of rising main & interconnection for Toria & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 625 Mtr.) | AE Sadar Sub-division |  | ORD/000435/2024-2025 | 320/MD | 29/01/2025 | 15/03/2025 | MAA SARADA ENTERPRISE | 6.43 | 0 | 0 | 0
Total | [13 empty] | 945.74 | 311.03 | 32.89