## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18502 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kalara & its adjoining Mouzas PWSS instead Radhakantapur its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000745/2022-2023 | 1263/MD | 23/06/2022 | 03/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.73 | 3.73 | 100 | 100
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18502 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000345/2023-2024 | 1684/W/MMD | 04/08/2023 | 25/01/2026 | ALPHA ENTERPRISE | 37.86 | 27.25 | 71.99 | 60
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18502 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 500 & 600 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,406 nos.) under JJM with allied work for Gopalnagar & Kalara PWSS in Daspur-I Block including supply of all labour & materials including Two (02) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000229/2023-2024 | 2953/MD | 17/08/2023 | 27/09/2025 | GOBINDA MAITY | 1693.15 | 0 | 0 | 20
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18502 | New | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 95/MD | 10/01/2023 | 10/01/2023 | Resource Division | 192.26 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18502 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 10/09/2024 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
6 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18502 | New | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 3336/MD | 25/11/2024 | 25/11/2024 | Resource Division | 17.48 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18502 | New | QUOTATION MONEY FOR KALARA WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/18502, APPLICATION NO 2004809520, REFERENCE ID 204352787, DASPUR CCC, WBSEDCL. |  |  | BILL/01638/2024-2025 | BP-2024-25-487 | 30/07/2024 | 30/07/2024 | WBSEDCL | 6.53 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18502 | New | QUOTATION MONEY FOR KALARA WATER SUPPLY SCHEME, T W NO II, JJM WORKS, SCHEME CODE SM/18502, APPLICATION NO 2004829551, REFERENCE ID 204362487,BLOCK- DASPUR-I, DASPUR CCC, WBSEDCL |  |  | BILL/01851/2024-2025 | BP-2024-25-543 | 07/08/2024 | 07/08/2024 | WBSEDCL | 3.01 | 0 | 0 | 0
Total | [13 empty] | 1964.44 | 30.98 | 1.58