## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Daspur, Block - Daspur-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000156/2021-2022 | 914/MD | 10/06/2021 | 20/06/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.88 | 3.88 | 100 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Daspur, Block - Daspur-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000197/2021-2022 | 930/MD | 14/06/2021 | 24/06/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.07 | 2.07 | 99.99 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000363/2023-2024 | 1691/W/MMD | 04/08/2023 | 06/07/2025 | P.K.ENGINEERING | 37.87 | 26.42 | 69.75 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,245 Nos.) under JJM with allied work for Augmentation of Daspur (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000250/2023-2024 | 3145/MD | 29/08/2023 | 28/09/2025 | GOBINDA MAITY | 1112.86 | 473.36 | 42.54 | 20
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 3339/MD | 25/11/2024 | 25/11/2024 | Resource Division | 117.64 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | QUOTATION MONEY FOR DASPUR AUGMENTATION, DIHIBALIHARPUR WATER SUPPLY SCHEME, T W NO IV , JJM WORKS, SCHEME CODE SM/18506, APPLICATION NO 2004809572, REFERENCE ID 204352799, DASPUR CCC, WBSEDCL |  |  | BILL/01636/2024-2025 | BP-2024-25-488 | 30/07/2024 | 30/07/2024 | WBSEDCL | 6.23 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | QUOTATION MONEY FOR DASPUR WATER SUPPLY SCHEME, T W NO 3, [ AUGMENTATION ] , JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/18506, APPLICATION NO 2004849405, REFERENCE ID 204373191, DASPUR CCC, WBSEDCL |  |  | BILL/02042/2024-2025 | C082441593739 | 29/08/2024 | 29/08/2024 | WBSEDCL | 5.2 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | Laying of rising main pipeline for Augmentation of Daspur (Zone-I & II) & its adj. mouzas Pipe W/S Scheme within block - Daspur-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000379/2024-2025 | 54/MD | 07/01/2025 | 08/03/2025 | GOBINDA MAITY | 20.06 | 0 | 0 | 80
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18506 | Augmentation | QUOTATION MONEY FOR DASPUR WATER SUPPLY SCHEME [ AUGMENTATION ], T W NO V, JJM WORKS, SCHEME CODE SM/18506, APPLICATION NO 2005016347, REFERENCE ID 204478563, DASPUR CCC, WBSEDCL |  |  | BILL/03891/2024-2025 | BP-2024-25-902 | 21/01/2025 | 21/01/2025 | WBSEDCL | 8.98 | 0 | 0 | 0
Total | [13 empty] | 1314.79 | 505.73 | 38.46