## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/18507 | New | Material Requisition To Resource Division |  |  | RTOR000253/2023-2024 | 1587/MD | 15/05/2023 | 15/05/2023 | Resource Division | 70.34 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/18507 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000350/2023-2024 | 1685/W/MMD | 04/08/2023 | 31/01/2024 | S.K.ENTERPRISE | 25.26 | 19.8 | 78.38 | 50
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/18507 | New | Quotation for new power connection at Barbasi T/W - I Within Khargpur - II Block, Application No - 2004975141 , Ref ID - 204452540 |  |  | BILL/03155/2024-2025 | C122403004364 | 04/12/2024 | 04/12/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/18507 | New | Quotation for new power connection at Barbasi T/W - II Within Khargpur - II Block, Application No - 2004970379 , Ref ID - 204449425 |  |  | BILL/03158/2024-2025 | C122403004056 | 04/12/2024 | 04/12/2024 | WBSEDCL | 3.06 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/18507 | New | Sinking of Tube wells, Construction of 400 CuM Capacity R.C.C Over Head Reservoirs (Over Raft / Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6,875 Nos.) for Jagannathchak & Barbasi Pipe W/S Scheme including 2 years O&M within Kharagpur-II Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000248/2023-2024 | 3101/MD | 25/08/2023 | 05/10/2025 | GOBINDA MAITY | 1932.69 | 637.14 | 32.97 | 25
Total | [13 empty] | 2034.71 | 656.94 | 32.29