## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | SM/18508 | New | Material Requisition To Resource Division |  |  | RTOR000061/2024-2025 | 3381/MD | 25/11/2024 | 25/11/2024 | Resource Division | 17 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | SM/18508 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of GOPALBANDH PWSS. REF CONSUMER ID-204269029, APPLICATION NO-2004675306 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00318/2024-2025 | BP-2024-25-71 | 24/04/2024 | 24/04/2024 | WBSEDCL | 0.29 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | SM/18508 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of GOPALBANDH PWSS. REF CONSUMER ID-204269014, APPLICATION NO-2004675316 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00313/2024-2025 | BP-2024-25-72 | 24/04/2024 | 24/04/2024 | WBSEDCL | 9.56 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | SM/18508 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 07/01/2026 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | SM/18508 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000343/2023-2024 | 1683/W/MMD | 04/08/2023 | 01/05/2025 | ALPHA ENTERPRISE | 25.24 | 0 | 0 | 20
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | SM/18508 | New | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, (HQ) Midnapur Division PHE Dte.for12(twelve)months.(Period From-01.01.2024 to 31.12.2024) | AE Sadar Sub-division,Assistant Engineer (HQ) | JE2 Sadar Sub-division,Junior Engineer (estimating section) | ORD/000580/2023-2024 | 925/AE/MSSD | 13/12/2023 | 13/12/2024 | NAFISA ENTERPRISE | 1.73 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | SM/18508 | New | Laying of rising main & interconnection for Gopal Bandh & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 435 Mtr.) | AE Sadar Sub-division |  | ORD/000414/2024-2025 | 195/MD | 17/01/2025 | 03/03/2025 | M/S. S.S. ENTERPRISE | 5.73 | 0 | 0 | 0
Total | [13 empty] | 5791.86 | 0 | 0