## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | RAUTMANI AND ITS ADJOINING MOUZAS PWSS | SM/18523 | New | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 1506/MD | 12/05/2023 | 12/05/2023 | Resource Division | 39.69 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | RAUTMANI AND ITS ADJOINING MOUZAS PWSS | SM/18523 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RAUTMANI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001436/2023-2024 | 3090/W/MMD | 29/11/2023 | 27/05/2024 | AMITAVA CHAKRABORTY | 25.24 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | RAUTMANI AND ITS ADJOINING MOUZAS PWSS | SM/18523 | New | Quotation for new power connection at Routhmoni PWSS T/W - I , Application no- 2004812911, Ref no : 204353062 |  |  | BILL/01579/2024-2025 | BP-2024-25-458 | 23/07/2024 | 23/07/2024 | WBSEDCL | 5.12 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | RAUTMANI AND ITS ADJOINING MOUZAS PWSS | SM/18523 | New | Quotation for new power connection at Routhmoni PWSS T/W - II Khargpur - II Block, Application No - 2004799376 , Ref ID : 204344493 |  |  | BILL/02017/2024-2025 | C082430203830 | 20/08/2024 | 20/08/2024 | WBSEDCL | 4.72 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | RAUTMANI AND ITS ADJOINING MOUZAS PWSS | SM/18523 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,186 Nos.) under JJM with allied work including 02 (Two) years Operation & Maintenance for Rautmani & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the distrist of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000240/2023-2024 | 3049/MD | 23/08/2023 | 05/06/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 876.48 | 63.63 | 7.26 | 15
Total | [13 empty] | 951.25 | 63.63 | 6.69