## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | SM/18524 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHARMA PUR AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000339/2023-2024 | 1680/W/MMD | 04/08/2023 | 31/01/2024 | SUBHASIS ROY | 27.34 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | SM/18524 | New | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 100/MD | 10/01/2023 | 10/01/2023 | Resource Division | 19.61 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | SM/18524 | New | Material Requisition To Resource Division |  |  | RTOR000054/2024-2025 | 3374/MD | 25/11/2024 | 25/11/2024 | Resource Division | 17.55 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | SM/18524 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of DHARMAPUR PWSS. REF CONSUMER ID-204188704, APPLICATION NO-2004559827, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/03734/2023-2024 | BP-2023-24-700 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.6 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | SM/18524 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of DHARMAPUR PWSS. REF CONSUMER ID-204240653, APPLICATION NO-2004634438, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPEERKUAI CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/04477/2023-2024 | BP-2023-24-847 | 14/03/2024 | 14/03/2024 | WBSEDCL | 7.59 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | SM/18524 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,760 nos.) under JJM with allied work for Dharmmapur PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000237/2023-2024 | 3040/MD | 22/08/2023 | 07/02/2026 | BANERJEE CONSTRUCTION | 939.5 | 209 | 22.25 | 28
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | SM/18524 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 05/01/2025 | M/S BIKASH DE | 6.3 | 0.14 | 2.17 | 50
Total | [13 empty] | 1021.5 | 209.13 | 20.47