## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | SM/18525 | New | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 65/MD | 09/01/2023 | 09/01/2023 | Resource Division | 17.57 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | SM/18525 | New | Material Requisition To Resource Division |  |  | RTOR000060/2024-2025 | 3380/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.06 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | SM/18525 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KHIRISHMUL PWSS. REF CONSUMER ID-204269069, APPLICATION NO-2004675308 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00316/2024-2025 | BP-2024-25-75 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | SM/18525 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KHIRISHMUL PWSS. REF CONSUMER ID-204269078, APPLICATION NO-2004675326, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00311/2024-2025 | BP-2024-25-74 | 24/04/2024 | 24/04/2024 | WBSEDCL | 6.61 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | SM/18525 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHIRISH MUL AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000341/2023-2024 | 1682/W/MMD | 04/08/2023 | 12/06/2025 | PADMA ENGINEERING CO. | 23 | 0 | 0 | 30
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | SM/18525 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,958 nos.) under JJM with allied work for Khirishmul PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000253/2023-2024 | 3148/MD | 29/08/2023 | 15/01/2026 | BANERJEE CONSTRUCTION | 1014.08 | 0 | 0 | 35
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | SM/18525 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 05/01/2025 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
8 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | SM/18525 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 09/02/2026 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
Total | [13 empty] | 1086.64 | 0 | 0