## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS | SM/18526 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHAKISHOR AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000359/2023-2024 | 1687/W/MMD | 04/08/2023 | 30/06/2025 | ORIENTAL ENGINEERING CO. | 27.35 | 0 | 0 | 80
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS | SM/18526 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (3,476 nos.) under JJM with allied work including 02 (Two ) Years Operation & Maintenance for Radhakishor & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000348/2023-2024 | 4000/MD | 06/10/2023 | 26/06/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1051.83 | 277.39 | 26.37 | 70
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS | SM/18526 | New | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 207/MD | 16/01/2023 | 16/01/2023 | Resource Division | 76.02 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS | SM/18526 | New | Material Requisition To Resource Division |  |  | RTOR000085/2024-2025 | 3437/MD | 25/11/2024 | 25/11/2024 | Resource Division | 21.41 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS | SM/18526 | New | Quotation for new power connection at Radhakishore PWSS T/W - I Khargpur - II Block, Application No - 2004799343 , Ref ID : 204344492 |  |  | BILL/02016/2024-2025 | BP-2024-25-585 | 20/08/2024 | 20/08/2024 | WBSEDCL | 4.95 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS | SM/18526 | New | Quotation for new power connection at Radhakishore PWSS T/W - II under KGP - II block , Application No- 2004799279, Ref No- 204344494 |  |  | BILL/01807/2024-2025 | BP-2024-25-525 | 06/08/2024 | 06/08/2024 | WBSEDCL | 6.95 | 0 | 0 | 0
Total | [13 empty] | 1188.51 | 277.39 | 23.34