## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | SINNIBAR PIPED WATER SUPPLY SCHEME | SM/18527 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,416 nos.) under JJM with allied work for Sinnibar PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000258/2023-2024 | 3232/MD | 11/09/2023 | 30/06/2026 | M/S. A.R. ENTERPRISE. | 917.01 | 0 | 0 | 40
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | SINNIBAR PIPED WATER SUPPLY SCHEME | SM/18527 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SINNIBAR PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000360/2023-2024 | 1688/W/MMD | 04/08/2023 | 16/10/2025 | SOUMEN ELECTRIC | 27.37 | 19.54 | 71.38 | 20
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | SINNIBAR PIPED WATER SUPPLY SCHEME | SM/18527 | New | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 104/MD | 10/01/2023 | 10/01/2023 | Resource Division | 22.51 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | SINNIBAR PIPED WATER SUPPLY SCHEME | SM/18527 | New | Material Requisition To Resource Division |  |  | RTOR000057/2024-2025 | 3377/MD | 25/11/2024 | 25/11/2024 | Resource Division | 21.04 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | SINNIBAR PIPED WATER SUPPLY SCHEME | SM/18527 | New | Electric quotation bill for TW No-I of SINNIBAR PWSS (Ref Consumer ID-204182338) |  |  | BILL/03341/2023-2024 | BP-2023-24-562 | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.23 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | SINNIBAR PIPED WATER SUPPLY SCHEME | SM/18527 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF SINNIBAR PWSS. REF CONSUMER ID-204211984, APPLICATION NO-2004590238, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/01455/2024-2025 | BP-2024-25-418 | 15/07/2024 | 15/07/2024 | WBSEDCL | 4.67 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | SINNIBAR PIPED WATER SUPPLY SCHEME | SM/18527 | New | Laying of rising main & interconnection for Sinnibar & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 675 Mtr.) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000389/2024-2025 | 61/MD | 07/01/2025 | 29/10/2025 | A-PLUS | 6.58 | 0 | 0 | 0
Total | [13 empty] | 1002.41 | 19.54 | 1.95