## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KUSUMDAHARI PIPED WATER SUPPLY SCHEME | SM/18531 | New | Material Requisition To Resource Division |  |  | RTOR000055/2024-2025 | 3375/MD | 25/11/2024 | 25/11/2024 | Resource Division | 11.51 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KUSUMDAHARI PIPED WATER SUPPLY SCHEME | SM/18531 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KUSUMDAHARI PWSS. REF CONSUMER ID-204269085, APPLICATION NO-2004675279, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00314/2024-2025 | BP-2024-25-77 | 24/04/2024 | 24/04/2024 | WBSEDCL | 4.8 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KUSUMDAHARI PIPED WATER SUPPLY SCHEME | SM/18531 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KUSUMDAHARI PWSS. REF CONSUMER ID-204269092, APPLICATION NO-2004675269, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00310/2024-2025 | BP-2024-25-76 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.88 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KUSUMDAHARI PIPED WATER SUPPLY SCHEME | SM/18531 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 07/04/2026 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KUSUMDAHARI PIPED WATER SUPPLY SCHEME | SM/18531 | New | Laying of rising main & interconnection for Kusumdahari & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 560 Mtr.) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000415/2024-2025 | 196/MD | 17/01/2025 | 03/03/2025 | M/S. S.S. ENTERPRISE | 6.2 | 0 | 0 | 0
Total | [13 empty] | 5758.7 | 0 | 0